## Overview
Overall Project
Group Name: | Arthub |  | Note : -
Mark : | 8
Student Percent (%) | 100%
No | Student ID | Student Name | Class Name | Student Percent | Mark | Note
1 | SE162024 | Lê Quyết Anh | NET1711 | 47% | 8
2 | SE170417 | Trần Thanh Minh Huy | NET1711 | 47% | 8
3 | SE151229 | Trương Thành Nhân | NET1711 | 6% | 1.0213

## Tasks
Task List
No | Task Name | Percent (%) | Student Name | Created At | Updated At | Status | Note
1 | Use case diagram | 100% | Lê Quyết Anh | 2024-01-10 | 2024-03-16 | Done
2 | Use case specification | 100% | Trần Thanh Minh Huy | 2024-01-10 | 2024-03-16 | Done
3 | Functional requirements | 100% | Trương Thành Nhân | 2024-01-11 | 2024-03-16 | Done
4 | Database Design | 100% | Lê Quyết Anh | 2024-01-29 | 2024-03-16 | Done
5 | Class Design | 100% | Trần Thanh Minh Huy | 2024-01-28 | 2024-03-16 | Done
6 | Sequence diagram | 100% | Lê Quyết Anh | 2024-01-28 | 2024-03-16 | Done
7 | Sequence diagram | 50% | Trương Thành Nhân | 2024-01-28 | 2024-03-16 | Proccess
7 | Sequence diagram | 100% | Trần Thanh Minh Huy | 2024-01-28 | 2024-03-16 | Done
8 | ERD | 100% | Lê Quyết Anh | 2024-01-28 | 2024-03-16 | Done
9 | ERD | 100% | Trần Thanh Minh Huy | 2024-01-28 | 2024-03-16 | Done
10 | Create Database | 100% | Lê Quyết Anh | 2024-01-28 | 2024-03-16 | Done
13 | Coding Login, Register page | 100% | Trần Thanh Minh Huy | 2024-01-28 | 2024-03-16 | Done
14 | Coding Home page | 100% | Trần Thanh Minh Huy | 2024-01-28 | 2024-03-16 | Done
15 | Coding Upload Artwork page | 100% | Trần Thanh Minh Huy | 2024-01-28 | 2024-03-16 | Done
16 | Coding Profile page | 100% | Trần Thanh Minh Huy | 2024-01-28 | 2024-03-16 | Done
17 | Coding Profile page | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
18 | Coding Comment function | 100% | Trần Thanh Minh Huy | 2024-02-15 | 2024-03-16 | Done
19 | Coding Artwork Detail page | 100% | Trần Thanh Minh Huy | 2024-02-15 | 2024-03-16 | Done
20 | Coding Balance page | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
21 | Coding Deposit and Withdraw function | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
22 | Coding Transaction Page for Admin | 100% | Trần Thanh Minh Huy | 2024-02-15 | 2024-03-16 | Done
23 | Coding Report Page for Admin | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
24 | Coding Post and comment component | 100% | Trần Thanh Minh Huy | 2024-02-15 | 2024-03-16 | Done
25 | Coding API Admin | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
26 | Coding API for Artwork | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
27 | Coding API for Balance | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
28 | Coding API for Post and Comment | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
29 | Coding API for Follow function | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
30 | Coding API for Authentication | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
31 | Coding API for Order Artwork | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
32 | Coding API for Rating function | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
33 | Coding API for Report function | 100% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | Done
34 | Intergate Payment Gateways | 0% | Lê Quyết Anh | 2024-02-15 | 2024-03-16 | None
34 | Preorder Page | 0% | Trần Thanh Minh Huy | 2024-02-15 | 2024-03-16 | None
33 | Coding API for Report function | 30% | Trương Thành Nhân | 2024-02-15 | 2024-03-16 | Proccess

## Final (hidden)
Overall Project
Group Name: | Arthub |  | Note : -
Max Mark : | 0
Student Percent (%) | 100%
Teacher Percent (%) | 100%
No | Student ID | Student Name | Class Name | Student (%) | Teacher (%) | Mark | Note
1 | SE160929 | Lê Quang Minh | NJS1601 | 15% | 15% | 0
2 | SE161130 | Nguyễn Minh Tú | NJS1601 | 21% | 21% | 0
3 | SE161087 | Mai Thanh Tâm | NJS1601 | 22% | 22% | 0
4 | SE161584 | Trần Hoàng Minh | NJS1601 | 21% | 21% | 0
5 | SE160191 | Nguyễn Hoàng Lam Trường | NJS1601 | 21% | 21% | 0

## Criteria (hidden)
Task List
Componets | Contribute | Mark | Code | Criteria Name | Rate | Mark | Total | Mandatory
Product | 40% | 0 | P1 | Scope - Coverage of objectives | 15% |  | 0 | Y
|  |  | P2 | UI/UX | 10% |  | 0 | N
|  |  | P3 | UI Validation | 5% |  | 0 | N
|  |  | P4 | Demo Flows 1 (Data Initiation) | 15% |  | 0 | Y
|  |  | P5 | Demo Flows 2 (Main Flows) | 25% |  | 0 | Y
|  |  | P6 | Demo Flows 3 (Dashboard & Reports) | 15% |  | 0 | N
|  |  | P7 | Using technology in system | 10% |  | 0 | N
|  |  | P8 | Using 3rd Services (Firebase Authen, Storage, SendMail, Push Notification…) | 5% |  | 0 | N
Process & Document | 50% | 0 | D1 | Requirements | 15% |  | 0 | N
|  |  | D2 | Prototype | 10% |  | 0 | N
|  |  | D3 | UseCase Diagram | 25% |  | 0 | Y
|  |  | D4 | Class Diagram | 20% |  | 0 | Y
|  |  | D5 | State Machine Diagram | 5% |  | 0 | N
|  |  | D6 | Activtiy Diagram | 25% |  | 0 | N
Presentation | 10% | 0 | PE1 | Slides quality & presentation style & Time management | 60% |  | 0 | Y
|  |  | PE2 | Inquiry Handling style | 40% |  | 0 | N